## Sheet1
Organization Name |  | University of Michigan
ARPA-E Award Number |  | DE-AR0000426
ARPA-E Program |  | REMOTE
WBS | Task/Milestone Description | Planned Start Date | Planned End Date | Milestone (y/n)
WBS | Name (task, subtask, milestone)
1 | Engineer pathways for anaerobic bioconversion methane to liquid fuels - John Leigh (U. Washington)
1.1 | Clone ANME MCR genes into Methanococcus maripaludis and verify expression | 2014-01-23 | 2014-06-01 | n
M1.1 | Confirm presence of introduced genes and expressed protein by RT-PCR and Western blot, and obtain at least 0.1 mg protein/g cell dw. | 2014-06-01 | 2014-06-01 | y
1.2 | Clone Methanothermobacter marburgensis MCR genes into M. maripaludis and verify expression | 2014-06-01 | 2014-11-01 | n
M1.2 | Confirm presence of introduced genes and expressed protein by RT-PCR and Western blot, and obtain at least 0.1 mg protein/g cell dw. | 2014-11-01 | 2014-11-01 | n
1.3 | Test for genetic complementation of MCR deletion mutation in M. maripaludis | 2014-11-01 | 2015-01-01 | n
M1.3 | Confirm activity of introduced enzymes by demonstrating viability of M. maripaludis MCR deletion mutants in expression strains | 2015-01-01 | 2015-01-01 | y
1.4 | Clone Methanosarcina and Methanosphaera methanol methyltransferase genes into M. maripaludis and verify expression | 2015-01-01 | 2015-05-01 | n
M1.4 | Confirm presence of introduced genes and expressed protein by RT-PCR and Western blot, and obtain at least 0.1 mg protein/g cell dw. | 2015-05-01 | 2015-05-01 | y
1.5 | Test for methanol methyltransferase activity in cell extract | 2015-05-01 | 2015-06-01 | n
M1.5 | Demonstrate activity of introduced enzymes by in vitro assay. Obtain 0.06 moles CH3OH/g cell dw/h. | 2015-06-01 | 2015-06-01 | y
1.6 | Test for metabolic conversion of methanol to methane by methanogenesis from methanol, OR demonstrate conversion of methane to methanol using labeled substrates | 2015-06-01 | 2015-07-01 | n
M1.6 | Demonstrate 2x10-4 umoles CH3OH to CH4/g total cell protein/second, OR show flux of CH4 to CH3OH (the latter will be limited at this stage due to thermodynamic limitations). | 2015-07-01 | 2015-07-01 | y
1.7 | Increase expression level of MCR | 2015-07-01 | 2017-01-01 | n
M1.7 | Obtain 50 mg MCR protein/g cell dw (10% of total cell protein). | 2017-01-01 | 2017-01-01 | y
1.8 | Clone genes for ATP sulfurylase and APS reductase into M. maripaludis and verify expression | 2015-07-01 | 2015-12-01 | n
M1.8 | Confirm presence of introduced genes and expressed protein by RT-PCR and Western blot, and obtain at least 0.1 mg protein/g cell dw. | 2015-12-01 | 2015-12-01 | y
1.9 | Assay for ATP sulfurylase and APS reductase activities | 2015-12-01 | 2016-02-01 | n
M1.9 | Demonstrate activity of introduced enzymes by in vitro assay. Obtain 5x10-5 umoles/g total cell protein/second. | 2016-02-01 | 2016-02-01 | y
1.1 | Clone sulfite reductase genes from related methanogens into M. maripaludis and verify expression | 2016-02-01 | 2016-04-01 | n
M1.10 | Confirm presence of introduced genes and expressed protein by RT-PCR and Western blot, and obtain at least 0.1 mg protein/g cell dw. | 2016-04-01 | 2016-04-01 | y
1.11 | Clone sulfite reductase genes from sulfate reducers into M. maripaludis and verify expression | 2016-04-01 | 2016-08-01 | n
M1.11 | Confirm presence of introduced genes and expressed protein by RT-PCR and Western blot, and obtain at least 0.1 mg protein/g cell dw. | 2016-08-01 | 2016-08-01 | y
1.12 | Assay for sulfite reduction to sulfide | 2016-08-01 | 2016-09-01 | n
M1.12 | Demonstrate activity of introduced enzymes by in vitro assay. Obtain at least 5x10-5 umoles/g total cell protein/second.. | 2016-09-01 | 2016-09-01 | y
1.13 | Manipulate expression of electron flow pathways as necessary. Introduce modified MCRs | 2016-09-01 | 2016-11-01 | n
M1.13 | Reach activities of sulfate to sulfide pathways of 1.25 umoles/g total cell protein/second. Demonstrate improved fluxes by introduction of modified MCRs | 2016-11-01 | 2016-11-01 | y
1.14 | Test for conversion of metane to methanol and optimize metabolic fluxes as needed | 2016-11-01 | 2017-01-01 | n
M1.14 | Achieve methane conversion to methanol at a rate of at least 1g CH4/g cell dw/hr (0.5g CH4/L/hr). | 2017-01-01 | 2017-01-01 | y
2 | Metabolic modeling and flux measurements - Nathan Price (ISB) |  |  | n
2.1 | Build genome scale flux balance and core metabolic flux models for M. marapaludis metabolism: Semi-automated reconstruction of M. maripaludis model using maximum liklihood orthology approach | 2014-01-23 | 2014-04-01 | n
2.2 | Genome scale flux balance and core metabolic flux models: Manual curation of M. maripaludis model based on biochemical, genetic, and physiological data from literature | 2014-04-01 | 2014-12-01 | n
M2.1 | Milestone: Deliver first genome-scale metabolic model capable of simulating growth and byproduct secretion with >75% accuracy | 2014-12-01 | 2014-12-01 | y
M2.2
2.3 | Genome scale flux balance and core metabolic flux models: Build detailed core metabolic network model to enable metabolic flux measurements | 2014-05-01 | 2015-02-01 | n
2.4 | Genome scale flux balance and core metabolic flux models: Integrate detailed core metabolic flux model with the genome-scale flux balance model | 2014-01-01 | 2015-02-01 | n
M2.2 | Milestone: Deliver first model of core metabolism in M. marapaludis with atom-level detail for molecular transformations as needed for flux measurements. | 2015-02-01 | 2015-02-01 | y
2.5. | Validate metabolic models against experimental data: Perform measurements of growth rates, substrate uptake rates, and byproduct secetion rates | 2014-02-01 | 2014-06-01 | n
2.6. | Validate metabolic models against experimental data: Perform time series metabolomics measurements in batch cultures | 2014-06-01 | 2014-11-01 | n
2.7. | Validate metabolic models against experimental data: Compare all measurements under different conditions to model simulation | 2014-11-01 | 2015-02-01 | n
2.8. | Validate metabolic models against experimental data: Iteratively improve the model as needed | 2015-02-01 | 2015-07-01 | n
M2.3 | Milestone: Deliver improved model that enables predictions with >85% predictive accuracy for knockout lethality, and <20% error for wildtype growth and byproduct yield predictions | 2015-07-01 | 2015-07-01 | y
2.9. | Use the models to guide strain engineering for methanol production: Introduce engineered pathways for methane to methanol and sulfate to sulfide into the integrated metabolic model | 2015-06-01 | 2015-07-01 | n
2.10. | Use the models to guide strain engineering for methanol production: Simulate expected product conversion yields and compare with experiment | 2015-07-01 | 2015-08-01 | n
M2.4 | Milestone: Deliver top 5-10 strain design predictions based on methanol yield to team for implementaton | 2015-08-01 | 2015-08-01 | y
2.11 | Use the models to guide strain engineering for methanol production: Evaluate alternative designs and identify additional alterations to help optimize metabolic fluxes for production of methanol | 2015-08-01 | 2015-10-01 | n
2.12 | Use the models to guide strain engineering for methanol production: Measure metabolic fluxes in engineered strains and compare distributions with the computed optimum | 2015-10-01 | 2016-01-01 | n
2.13. | Use the models to guide strain engineering for methanol production: Iteratively design and refine network and test engineered strain to optimize for methanol production | 2016-01-01 | 2016-10-31 | n
M2.5 | Milestone: Provide 3 best engineered strains with highest methanol production based on metabolic modeling | 2016-10-31 | 2017-01-01 | y
3 | Biochemical optimization of enzymes involved in methane conversion to methanol - Steve Ragsdale (U. Mich)
3.1 | Determine endogenous M. maripaludis activities of MCR, HDR and Methyltransferase | 2014-01-23 | 2014-04-01 | n
3.2 | Methyl-SCoM Reductase (MCR): Characterize kinetic parameters, assess kinetic bias, and measure biophysical properties of heterologously expressed M. marburgensis and ANME MCRs in the forward & reverse direction | 2014-02-01 | 2014-12-01 | n
M3.1 | Milestone: Deliver MCR witha specific activity for the purified protein of at least 5 units/mg (after activation) in the methane synthesis direction and 0.5 units/mg in methane oxidation. | 2014-12-01 | 2014-12-01 | y
3.3. | Heterodisulfide Reductase (HDR): Determine kinetic parameters of the native and ANME HDRs in the forward & reverse direction | 2014-01-23 | 2014-07-01 | n
M3.2 | Milestone: choose the HDR with a specific activity of at least 10 units/mg. | 2014-07-01 | 2014-07-01 | y
3.4. | Methyl-SCoM:Methanol Methyltransferase (MeTr): Determine kinetic and physical properties of the heterologously expressed MeTr in the forward & reverse direction | 2014-12-01 | 2015-12-01 | n
M3.3 | Milestone: choose the MeTr with an activity of >10 units/mg for methanol production from methyl-SCoM | 2015-12-01 | 2015-12-01 | y
3.5. | Sulfate to sulfide module (ATP sulfurylase, APS reductase and sulfite reductase): Measure background endogenous SO4-to-sulfide activity | 2015-07-01 | 2015-11-01 | n
3.6. | Sulfate to sulfide module: Purify and assess kinetic and physical properties of heterologously expressed ATP sulfurylases | 2015-11-01 | 2016-08-01 | n
M3.4 | Milestone: choose the ATP Sulfurylase with a specific activity of at least 10 units/mg. | 2016-08-01 | 2016-08-01 | y
3.7. | Sulfate to sulfide module: Purify and assess kinetic and physical properties of heterologously expressed APS Reductase | 2016-04-01 | 2016-11-01 | n
M3.5 | Milestone: choose the APS Reductase with a specific activity of at least 10 units/mg. | 2016-11-01 | 2016-11-01 | y
3.8. | Sulfate to sulfide module: Purify and assess kinetic and physical properties of heterologously expressed Sulfite Reductase | 2016-06-01 | 2016-12-01 | n
M3.6 | Milestone: choose the Sulfite Reductase with a specific activity of at least 10 units/mg. | 2016-12-01 | 2016-12-01 | y
3.9. | Ensure that the chosen sulfate to sulfide enzymes couple to give predicted flux - in vitro and in vivo | 2016-09-01 | 2017-01-01 | n
3.10. | Substitute enzymes from a single host if necessary - make adjustments based on in vivo flux measurements | 2016-09-01 | 2017-01-01 | n
M3.7 | Milestone: choose enzymes for the sulfate-to-sulfide module based on highest activity (>10 units/mg) | 2017-01-01 | 2017-01-01 | y
4 | Molecular modeling of the ANME MCR and other enzymes involved in GTL - Dayle Smith (PNNL)
4.1 | Build classical physics potential energy model for MCR inter-atomic interaction potentials: Derive atom-centered charges, equilibrium coordinates and force constants for the four non-protein molecules F430, CoBSH, SCoM, CoBS-SCoM | 2014-01-23 | 2014-07-01 | n
M4.1 | Milestone: Reproduce experimental MCR structure 1MRO.pdb with a root-mean-squared deviation of less than 10 Ångstroms. | 2014-07-01 | 2014-07-01 | y
4.2 | Apply potential energy function to identify amino acids that contribute to substrate binding thermodynamics (enthalpic, entropic, solvent and steric contributions): Perform > 100 ns explicit-solvent molecular dynamics simulations (MD) for solvated proteins in reactant and product states, Run trajectory analyses to calculate hydrogen bond networks, per-residue fluctuations, interaction potential energies, and Perform free energy perturbation calculations for point-mutations associated with Aim 3. | 2014-07-01 | 2015-10-01 | n
M4.2 | Milestone: Identification of at least 10 amino acids modulating substrate binding | 2015-10-01 | 2015-10-01 | y
4.3 | Determine MCR reaction pathways and reversibility as dependent on identified key amino acids from Aim 3 and task 4.2: Calculate and compare reaction pathway activation energies in methanogenic MCR for organometallic and radical pathways using a more extensive and accurate model than studies previously published | 2015-10-01 | 2016-03-01 | n
M4.3 | Milestone: Validate activation energies in the two pathways using experimental data from Ragsdale’s lab to reach agreement within 5 kcal/mol | 2016-03-01 | 2016-03-01 | y
4.4. | Predict effects of site-specific substitutions within methanogenic and methanotrophic (ANME) MCR on activation energies | 2016-01-01 | 2016-08-01 | n
M4.4 | Milestone: Validate changes in activation energies for amino acid substitutions to reach agreement to within 5 kcal/mol with data from Ragsdale’s lab. | 2016-08-01 | 2016-08-01 | y
4.5 | Predict effects of site-specific substitutions within methanogenic and methanotrophic (ANME) MCR on reaction reversibility | 2016-08-01 | 2017-01-01 | n
M4.5 | Milestone: Validate activation energies against those from Ragsdale’s lab to reach agreement within 5 kcal/mol. This will quantitatively establish the catalytic role of specific point-mutations on reaction reversibility. | 2017-01-01 | 2017-01-01 | y
y
5 | Technology Transfer and Intellectual Property: Work with Dr. Nadine Wong and others in Univ Mich. OTT to address IP and technology transfer matters related to the project team. |  |  | n
5.1. | Develop an IP sharing agreement among U. Mich, U. Washington, PNNL, and ISB | 2014-01-23 | 2014-04-01 | n
M5.1. | Milestone: Reach agreement and sign an IP sharing agreement among U. Mich, U. Washington, PNNL, and ISB | 2014-04-01 | 2014-04-01 | y
5.2. | Hire OTT fellow(s) to look at the ARPA-E REMOTE proposal and assess the relevant existing current patent landscape. | 2014-01-01 | 2014-04-01 | n
M5.2. | Milestone: Develop a profile of the existing patents related to methane to methanol (and GTL) biotechnology. | 2014-04-01 | 2014-04-01 | y
M5.3. | Milestone: File provisional patent for our plan to convert methane to methanol. | 2014-04-01 | 2014-04-01 | y
5.3. | Technology to Market Plan: Work with Dr. Nadine Wong and Fellows from OTT and Tech Transfer Consultants (above) to develop Tech to Market Plan | 2014-01-23 | 2014-07-01 | n
M5.4. | Milestone: Develop tech to market plan | 2014-07-01 | 2014-07-01 | y
5.4. | Market analysis: Use fellows within the OTT Fellows program to conduct market assessment of the technology area relevant to the conversion of methane to methanol and other liquid fuels | 2014-07-01 | 2014-10-01 | n
M5.5. | Milestone: Develop a document that assesses the market for conversion of methane to methanol and to butanol (GTL). | 2014-10-01 | 2014-10-01 | y
5.4. | Partner/funding outreach and engagement: Work through the Univ of Michigan Office of Technology Transfer (OTT) to identify and then hire an independent consultant for scouting and forging relationships with technology partners. During the first quarter, we will identify consultant candidates with the thought that that person would be onboard by the 2nd quarter and ramping up from there on. | 2014-01-23 | 2014-07-01 | n
M5.6. | Milestone: Hire an independent T2M Consultant to oversee the tech-to-market plan and forge relationships with technology partners. | 2014-07-01 | 2014-07-01 | y
5.5. | Partner/funding outreach and engagement: Develop a pitch deck. Ppt presentation tailored to use in meetings with potential partners, funders, etc. Slides would focus more on the market/commercial aspect rather than the technical. This would include market size, value proposition etc. | 2014-10-01 | 2015-02-01 | n
M5.7. | Milestone: Develop a pitch deck | 2015-02-01 | 2015-02-01 | y
5.6. | Partner/funding outreach and engagement: Travel to the annual ARPA-E summit. | 2016-04-01 | 2016-04-01 | n
5.7. | Partner/funding outreach and engagement: Hire graduate student fellow(s) at OTT3 to develop a preliminary list of companies with technology in the methane to methanol and methanol to fuels areas. OTT and UM have ongoing relationships with several target companies such as BASF, Dow Chemical and can be used to initiate discussions with those partners. | 2014-08-01 | 2015-02-01 | n
M5.8. | Milestone: Meet with potential industrial partners. | 2015-02-01 | 2015-02-01 | y
5.8. | Partner/funding outreach and engagement: Begin developing proposals for industrial and federal funding, based on the analysis of target companies and federal funding options. | 2015-02-01 | 2016-12-01 | n
M5.9. | Milestone: Write proposal for follow-up funding of the project. | 2015-08-01 | 2015-08-01 | y
5.9. | Partner/funding outreach and engagement: Involve OTT to negotiate the confidentiality and material transfer agreements, work with ORSP to negotiate IP terms within a sponsored research agreement. | 2015-07-01 | 2016-12-01 | n
5.10. | Technoeconomic analysis: Develop a technoeconomic model based on the model that Ramon used when he developed the REMOTE program | 2014-06-01 | 2016-10-01 | n
M5.10 | Milestone: Adjust the technoeconomic model to fit the methane-to-methanol proposal so that it is ready for data inputs | 2014-09-01 | 2014-09-01 | y
M5.11. | Milestone: Add data to the technoeconomic model and perform sensitivity analysis | 2015-09-01 | 2015-09-01 | y
M5.12. | Milestone: Complete the technoeconomic model | 2016-12-01 | 2016-12-01 | y
Formulas:
Planned Start Date = [Planned End Date, row above]